## 2023-4 WP Detail
Task | Oct-Nov-Dec 2023 | Jan-Feb-Mar 2024 | Ap-May-Jun 2024 | Jul-Aug-Sept 2024 | Oct-Nov-Dec 2024
Lead Entity for Salmon Recovery
Task 1: Project Development Identify, review, and submit salmon habitat project list for 2023 Salmon Recovery Funding Board and Puget Sound Acquisition and Restoration Funds. This tasks includes the whole grant round process and committee involvement. | x | x | x | Project list uploaded to PRISM | New call for projects
Task 2: Salmon Recovery Portal Add and track projects in Salmon Recovery Portal, participate in SRP Action Team, establish goals for umbrella projects (NEW) | x | x | x | x | x
Task 3: Outreach Build community support through education, committee member outreach, and landowner recruitment, and project sponsor recruitment (includes social media, website, events) | x | x | x | x | x
Task 4: East Kitsap Steelhead Recovery Plan Implementation, Salmonid Strategy, 4ywp Updates Participate in the implementation of the recovery chapter for the East Kitsap DIP for the Puget Sound Steelhead Recovery Plan, East Kitsap Chapter; update and refine the 4 Year Work Plan; Update Salmon Recovery Strategies | x | x | x | 4yr wp due early Aug | x
Local Integrating Organization (LIO)
Task 1: Organize, Support, Administer, Facilitate, and Coordinate a Local Integrating Organization Arrange and facilitate meetings, maintain website, attend regional LIO meetings, work with Lead Entity, ECB Forum (next in 2024) and advance outcomes, work with the BIL team, support opportunities for non-tribal LIO staff and committee members to understand treaty and sovereign rights of tribal nations. | x | x | x | x | x
Task 2: Participate in the Action Agenda Team Educate members and partners about the AA Facilitate updates, agenda items, and presentations to support AA implementation strategies and actions; support adaptive management of current version and development of future version and engage community in the process; contribute to LIO Collective Project | x | x | x | x | x
Task 3: Performance Management Admin, progress reports, billing | x | x | x | x | x
Task 4: Ecosystem Recovery Plan update and Adaptive Management Conservation Standards and/or Miradi training; annual ERP update to committees and Partnership; PS Info and AA Online Explorer materials review | Webmap tool and updated ERP | Webmap tool and updated ERP | Webmap tool and updated ERP | Final draft | Plan adoption
LIO Task 5: Tailor LIO coordination to Implement the Action Agenda and Support Unique Vision and Goals of LIO (seven potential subtasks)
Pursue and articulate EEJ in the LIO context Incorporate into all tasks 1-5 e.g., create effective and meaningful participation in LIO activities, consider underserved and underrepresented communities when developing projects and prgrams | Plan 2023 trainings (possibly Government to Government)
Work with committees to address and remove barriers to implementation (i.e., Derelict vessels, failing septic systems and water quality, integration of salmon and ecosystem recovery in local jurisdiction planning work.) Define barriers, develop solutions, and implement. (Could include workforce devlopment.) | Discuss/develop project proposals/NEP
Pursue Funding for 2022-2026 Action Agenda Implementation (Build capacity to compete for funding) | Invite SILs to present on upcoming National Estuary Program funding opportunities | ID and prioritize projects and programs for National Estuary Program funding | Work with PSP's funding team for Bipartisan Infrastructure Law Funding | Develop sequenced list for funding, leverage opportunities and resources, develop strategic grant proposals
Incorporate planning tools to improve and refine local planning (e.g., Structured Decision Making, Alternative Scenarios and/or other pre-approved approach in local planning)
Support LIO participation in regional planning and coordinating groups by advocating for local priorities (PSEMP, Action Agenda Coordination Group, more) | x | x | x | x | x
Inform and educate local decision makers on work of the LIO | x | Environmental Programs Consortium monthly coordination, ECB, Executive Committee |  |  | x
Support behavior change, public awareness, incentive, and/or compliance projects and programs (support ECO Net and similar) (Work with committees to identify outreach and education activities aligned with both the LIO Plan AND 2022-2026 AA) | Salmon Tours, Signage - including at Kitsap Golf and Country Club | Salmon Tours, derelict vessels, Natural Resources as an Asset, Water Typing, Shore Friendly