## 1. Introduction
Curley Creek Watershed Assessment Action Area Prioritization
Final V1 June 30, 2021
Background
The Curley Creek Watershed Assessment categorized the Curley Creek watershed into 31 Action Areas, and provided recommendations to protect and restore watershed, riparian, floodplain and stream processes and habitat conditions for salmonids. This workbook details the prioritization process used to rank Action Areas and associated recommendations identified in the Watershed Assessment. The prioritization process was led by Mid Sound Fisheries Enhancement Group with funding from the National Estuary Program, and technical advice and guidance from the project partners: • Ali Erskine, Great Peninsula Conservancy • Brittany Gordon, Washington Department of Fish and Wildlife • Carin Anderson, Kitsap Conservation District • Dana Coggon, Kitsap Noxious Weed Control Board • Erik Steffens, Great Peninsula Conservancy • Jamie Glasgow, Wild Fish Conservancy • Kathie Peters, Kitsap County • Marty Ereth, Pierce County • Steve Todd, Suquamish Tribe • Tom Ostrom, Suquamish Tribe • Zack Holt, City of Port Orchard This project has been funded wholly or in part by the United States Environmental Protection Agency under assistance agreement PC-01J22301 through the Washington Department of Fish and Wildlife. The contents of this document do not necessarily reflect the views and policies of the Environmental Protection Agency or the Washington Department of Fish and Wildlife, nor does mention of trade names or commercial products constitute endorsement or recommendation for use.
Approach
The Watershed Assessment presented a framework to prioritize action areas. Across four workshops, the partner group adapted and expanded on the initial framework to further differentiate the benefits of each project. The criteria used, along with descriptions of why criterion were included or excluded, are presented in Sheet 7. Each criterion was scored, and the scores were summed to assign a Benefit Score and Implementation Score. To rank the Action Areas: 1. Action Areas were sorted by Benefit Score (highest Benefit Score at the top) 2. Action Areas with equal Benefit Scores were sorted by Implementation Score (highest Implementation Score at the top) 3. Implementation considerations were reviewed to identify Action Areas that should be clustered, or Action Areas where sequencing considerations meant Actions should be moved higher or lower on the ranked list Partner feedback highlighted the importance of being both strategic and opportunistic in pursuing recovery actions. The third step in the ranking process allows the group to move projects higher or lower on the ranked list based on implementation considerations to allow flexibility to prioritize the most feasible projects, while also considering the benefit scores. This ranking is based on available information, and is design to be a flexible template that can be updated as new information becomes available or new opportunities are identified.
Navigation
This workbook is structured in the following sheets: • Sheet 2 presents the ranked Action Area list. • Sheets 3 – 6 summarizes the recommended actions and presents the scored criteria for each Action Area. This information can also be viewed in the webmap at https://www.midsoundfisheries.org/curley-creek-prioritization-draft-v3/ (password CurleyCreekPartners). • Sheet 7 defines the criteria used, and describes the rationale for including or excluding criteria from the assessment. The Curley Creek Watershed Assessment can be accessed through the links below. Refer to Section 6 for full project descriptions (beginning electronic page 107 if using pdf viewer).
Curley Creek Watershed Assessment and Restoration Plan
Appendix A Field Reconnaissance
Appendix B Data Inventory
Appendix C HRCD Maps
Appendix D Wetland Maps
Appendix E Canopy Height Maps
Appendix F Lidar REM
Appendix G WDFW Fish Passage Reports
Appendix H Action Area Maps
Appendix I Prioritization Framework

## 2. Ranking
Action Area Ranking
The following process was used to rank Action Areas: 1. Action Areas were sorted by Benefit Score (highest Benefit Score at the top) 2. Action Areas with equal Benefit Scores were sorted by Implementation Score (highest Implementation Score at the top) 3. Action areas were moved higher or lower on the list based on implementation considerations.
|  |  |  | Key: |  | Blue - Mid Sound to assess feasibility | Green - AA Recommendations in progress
Ranking | Project Type | Action Area | Benefit Score | Implementation Score | Combined Score | Additional Ranking Considerations | Next Steps
1 | Other | (28) Long Lake Shoreline | hi | 6 | 6 |  | Proposed - Mid Sound to start conversations with aim to create roadmap to tackle lake issues
2 | Passage | (12) Salmonberry Creek Crossing at Clover Valley Road SE | 15 | 9 | 24 | Moved to the top barrier project. Seond highest benefit project is a barrier upstream of this. This downstream barrier should be addressed first. | Proposed - Mid Sound to assess feasiblity.
3 | Passage | (14) Salmonberry Creek Crossing at SE Baker Road | 18.5 | 9 | 27.5 |  | Proposed - Mid Sound to assess feasiblity
4 | Other | Watertyping and Enforcement | 16 | 7 | 23 |  | In progress: WFC
5 | Passage | (17) Salmonberry Creek Crossing at SE Sedgwick Road | 13 | 8 | 21 |  | In progress: This is planned to be addressed by WSDOT 2021-2023.
6 | Protection | (2) Curley Creek Estuary to Sedgwick Road | 11 | 7 | 18 |  | In progress: GPC Active in this reach.
7 | Passage | (7) Unnamed Stream 15.0187 to Locker Road | 10 | 11 | 21 |  | In progress: Conservation District
8 | Protection | (25) Cool Creek upstream of Phillips Road | 10 | 8 | 18
9 | Protection | (4) Banner Creek (15.0186) to Sedgwick Road | 9 | 9 | 18
10 | Protection | (09) Unnamed Stream 15.0187 near Frog Pond Road | 9 | 9 | 18
11 | Channel Complexity | (16) Salmonberry Creek from Cool Creek confluence to Sedgwick Road | 8 | 9 | 17 | Prioritized above Channel Complexity projects with slightly higher score due to feasibility of implementation. There is a single landowner for this site, who has previously expressed interest in a project. Clustered with AA24 (same landowner). | Proposed - Mid Sound to assess feasiblity
11 | Channel Complexity | (24) Cool Creek Alluvial Fan Downstream of Phillips Road | 5 | 7 | 12 | Clustered with AA16 (same landowner). | Proposed - Mid Sound will assess if there is efficiency in combining this project with AA16.
12 | Channel Complexity | (3) Curley Creek Upstream of Sedgwick Road to Long Lake | 9 | 8 | 17
13 | Protection | (15) Salmonberry Creek from Baker Road to Cool Creek confluence | 9 | 7 | 16
14 | Channel Complexity | (19) Salmonberry Creek from Salmonberry Road to Constructed Side Channel Ponds | 9 | 6 | 15
15 | Protection | (31) Wetland Complex at SE corner of Long Lake | 8 | 10 | 18
16 | Protection | (30) Additional Tributaries draining to Long Lake | 8 | 8 | 16
17 | Protection | (10) Headwaters of Unnamed Stream 15.0187 | 8 | 7 | 15
18 | Protection | (08) Unnamed Stream 15.0187 in Ravine Upstream of Locker Road | 8 | 7 | 15
19 | Passage | (29) Upper Curley Creek | 7 | 11 | 18
20 | Passage | (5) Banner Creek (15.0186) Crossing at Sedgwick Road | 7 | 11 | 18
21 | Channel Complexity | (23) Salmonberry Creek at Howe Farm County Park | 7 | 10 | 17
22 | Protection | (18) Salmonberry Creek between Sedgwick Road and Salmonberry Road | 7 | 8 | 15
23 | Protection | (27) Tributary Channels Draining Urban Growth Area | 7 | 8 | 15
24 | Protection | (06) Banner Creek (15.0186) Upstream of Sedgwick Road | 7 | 8 | 15
25 | Protection | (13) Salmonberry Creek from Clover Valley Road to Baker Road | 7 | 7 | 14
26 | Passage | (22) Salmonberry Creek Crossing at Long Lake Road | 6 | 10 | 16 | Clustered with 21 - barrier projects located close together. | Clustered with 21 - barrier projects located close together.
26 | Passage | (21) Salmonberry Creek Crossing at Private Road Downstream of Long Lake Road | 6 | 10 | 16 | Clustered with 22 - barrier projects located close together. | Clustered with 22 - barrier projects located close together.
27 | Channel Complexity | (26) Cool Creek Downstream of Baker Road (Ashby Farm) | 5 | 8 | 13
28 | Channel Complexity | (20) Salmonberry Creek from Constructed Side Channel Ponds to Long Lake Road | 5 | 8 | 13
29 | Channel Complexity | (11) Salmonberry Creek Outlet at Long Lake | 4 | 6 | 10

## 3. Channel Complexity
Project Description |  |  |  |  | Benefit Criteria | [9 empty] | Implementation Criteria
Action Area (AA) | Notes WA: Watershed Assessment, ST: Steelhead Recovery Plan | Steelhead Recovery Plan Category | Primary Strategy | Secondary Strategies | Tier | Benefit Category | Project Type | Scale 1 point per 1000m or 10 acre project footprint | Habitat Quality 3 = Low 2 = Medium 1 = High | Continuity 3 = Fills gap between high quality habitats 2 = Adjacent high quality habitat 1 = Not adjacent high quality habitat | Education | Benefit Notes | Target Species | BENEFIT SCORE | Sequencing Score 4 = required for upstream project 3 = increases benefits of upstream project 2 = Standalone or Cluster 1 = Requires downstream project | Response Time 3 = Short 2 = Moderate 1 = Long | Complexity 4 = Low 3 = Moderate 2 = High 1 = Very High | Estimated Cost | Implementation Notes | IMPLEMENTATION SCORE
(16) Salmonberry Creek from Cool Creek confluence to Sedgwick Road | WA: Creek channelized and straightened. Previously golf course, now botanical gardens. Disconnected floodplain is flat and overgrown with reed canary grass. ST: In order for restoration of riparian vegetation and floodplain protection to occur, land needs to be acquired through conservation easements. Restoration will encourage wood recruitment and broaden the channel migration zone and improve floodplain health. Additional info from WFC 4/27/2021: There is a failed steel bridge located just south of Salmonberry creek’s crossing of SW Sedgwick Rd on a small piece of property owned by Steven Childers. The right bank footings of this bridge have eroded, and the right side of the bridge is resting on the streambed. The bridge does not appear to limit fish passage, at least at the time of the survey, but it would probably be a good idea to remove it before the entire structure falls into the channel. | Channel Complexity | Channel Restoration | Protection Riparian Wood | Tier 1 | B Medium Benefits | 1 | 2 | 3 | 2 | 0 | SCALE: Mainstem only: 800m; 21.4 acres Including connecting tributaries: 800m NOTES: Create new and improve existing habitat in 660m in lower third of Salmonberry Creek. Riparian cover to reduce water temperatures. | All | 8 | 1 | 2 | 4 | 2 | SEQUENCING: Requires downstream project Barrier at AA14 (Baker Road) RESPONSE TIME: Side channel / meanders / wood placement immediately benefits processes. Detect improved survival within 5 years. COMPLEXITY: 660m within 1 parcel, plus two others in action area. | 9
(3) Curley Creek Upstream of Sedgwick Road to Long Lake | ST: The stream channel will be actively modified to move the stream out of the artificial ditch, and improve channel complexity. Restoration of riparian vegetation will complement this work. Acquire land for conservation. | Channel Complexity | Channel Restoration | Protection Riparian Wood Beaver Management Passage | Tier 1 | A Highest Benefits | 1 | 3 | 3 | 2 | 0 | SCALE: Mainstem only: 1,600m 27 acres Including connecting tributaries: 4,400m; 30.1 acres NOTES: Used by all migrating salmonids. Lots of room for improvement. Create new habitat plus improve existing habitat. Would contribute to temperature improvements for all of Curley Creek. | All | 9 | 2 | 2 | 2 | 2 | SEQUENCING: Standalone No downstream barriers. RESPONSE TIME: Side channel / meanders / wood placement give immediate additional habitat. Riparian restoration more long term benefits. COMPLEXITY: Approx. 12 private landowners total. Good potential for smaller project with just 2-4 landowners. | 8
(26) Cool Creek Downstream of Baker Road (Ashby Farm) | WA: 1000ft segment channelized with riparian plantings. ST: The landowner of this property has previously taken steps to restore riparian vegetation and exclude cattle, but this project proposes to restore the stream corridor with wood placements and additional riparian vegetation. | Channel Complexity | Channel Restoration | Protection Riparian Wood | Tier 2 | C Lowest Benefits | 1 | 1 | 2 | 1 | 0 | SCALE: Mainstem only: 300m, 0.6 acres Including connecting tributaries: 300m, 0.6 acres NOTES: Previous work has achieved benefits. Proposed project would be incremental. |  | 5 | 1 | 2 | 3 | 2 | SEQUENCING: Requires downstream project Barrier at AA14 (Baker Road). Barrier at Sedgwick Road planned for replacement 2021-2023. RESPONSE TIME: Wood placement, riparian planting. COMPLEXITY: 1 - 2 private landowners | 8
(24) Cool Creek Alluvial Fan Downstream of Phillips Road | WA: Upper segment of alluvial fan is forested; recommended for protection and wood placement. Lower segment is channelized into ditch; recommended re-routing, riparian planting. Complete in tandem with Botanical Gardens (AA16). ST: This project will place large woody debris and move the channel out of a ditch. Additionally beaver will be encouraged to establish in this area. | Channel Complexity | Channel Restoration | Protection Riparian Wood | Tier 1 | B Medium Benefits | 1 | 1 | 1 | 2 | 0 | SCALE: Mainstem only: 700m, 9.9 acres Including connecting tributaries: 700m, 9.9 acres NOTES: Total project area 750m. Includes upstream forested section needing protection and wood placement; and downstream section where channel needs to be moved out of ditch. | Coho Chum Steelhead Cutthroat | 5 | 1 | 2 | 2 | 2 | SEQUENCING: Requires downstream project Barrier at AA14 (Baker Road). Barrier at Sedgwick Road planned for replacement 2021-2023. Cluster with AA16 because share a property owner (botanic garden). RESPONSE TIME: Side channel / meanders give immediate additional habitat and restore habitat forming processes over time. COMPLEXITY: 6 parcels, but could do a portion of project with only 3 parcels - one also includes AA16 (golf course) | 7
(19) Salmonberry Creek from Salmonberry Road to Constructed Side Channel Ponds | ST: Previous restoration actions were completed in 2004, but roughly 1,000 feet of the stream has not been restored. WA: The segment upstream of Salmonberry Road was previously cleared of riparian vegetation and channelized in a ditch crossing agricultural fields (Figure 6-12). Restoration actions completed in 2004 established conservation easements and created a complex of side channel ponds. There is an approximately 1,000 foot segment of the stream corridor between Salmonberry Road and the constructed side channel ponds that has not been treated and remains impaired by past impacts. Additional info and actions recommended in June 7, 2021 partner meeting: This is a really important area – the main rearing, overwintering habitat for Coho in the watershed, and important headwater functions. There is a lot of beaver activity. There are private ponds with warm water species and unpermitted landowner activity. There is a risk of these predator species connecting with Salmonberry Creek. One landowner has been in trouble for unpermitted work, even on properties with easements. This reach would benefit from more protection. | Channel Complexity | Channel Restoration | Protection Riparian Wood | Tier 1 | B Medium Benefits | 1 | 4 | 2 | 2 | 0 | SCALE: Mainstem only: 1,600m, 42.2 acres; Including connecting tributaries: 5,400m, 47.9 acres. NOTE: Identified as a very important reach for coho overwintering and rearing. | All | 9 | 1 | 2 | 1 | 2 | SEQUENCING: Requires downstream project Barrier at AA14 (Baker Road). Barrier at Sedgwick Road planned for replacement 2021-2023. RESPONSE TIME: Side channel / meanders / wood placement give immediate additional habitat. Riparian restoration longer response time. COMPLEXITY: Area yet to be restored has 8 parcels. No parcels cover both sides of stream (i.e. creek is parcel boundary). Plus approx 10 more unprotected parcels, and a number of protected parcels. | 6
(23) Salmonberry Creek at Howe Farm County Park | WA: 1000ft segment with very narrow riparian corridor. Opportunities to expand riparian buffer and install wood structures. Trail crossing is a fish passage barrier. Partner meeting June 7, 2021 (Brittany Gordon): Beaver activity has resolved the fish passage barrier; that area is flooded now. Concerns about bacteria in dog park. | Not listed | Riparian | Wood Passage | Tier 1 | B Medium Benefits | 1 | 2 | 2 | 1 | 1 | SCALE: Mainstem only: 1,700m, 13.3 acres Including connecting tributaries: 2,200m, 14 acres NOTES: Riparian restoration would increase shading and potential for wood recruitment. BONUS POINTS: 1 point for public engagement opportunity of project on actively used public land. | Coho Cutthroat | 7 | 1 | 2 | 4 | 3 | SEQUENCING: Requires downstream project Multiple partial barriers downstream on Salmonberry Creek. RESPONSE TIME: Passage project would give immediate benefit. Riparian restoration long term. COMPLEXITY: Public landowner. | 10 | 999390?
(11) Salmonberry Creek Outlet at Long Lake | WA: This area is an important transition zone. Existing outlet channel crosses 3 residential properties, and has minimal riparian cover. Restoration of processes may not be compactible with existing land use. Would include removing constraints to lateral channel migration, large wood installation and planting riparian buffer. Potential for riparian planting and small wood placement with existing landowners. ST: In order for restoration of riparian vegetation and floodplain protection to occur, land needs to be acquired through conservation easements. Restoration will encourage wood recruitment and broaden the channel migration zone and improve floodplain health. | Land Use | Protection | Riparian Channel Restoration Wood | Tier 1 | A Highest Benefits | 1 | 1 | 1 | 1 | 0 | SCALE: Mainstem only: 100m, 2.9 acres Including connecting tributaries: 100m, 2.9 acres | All | 4 | 2 | 2 | 1 | 1 | SEQUENCING: Standalone Located immediately downstream of first Salmonberry Creek barrier. RESPONSE TIME: Restoration of lateral migration moderate response. Establishing riparian vegetation longer response. COMPLEXITY: Approximately 4 landowners. Would need to acquire properties / change land use to do the full project. | 6 | 1 - High | Full project requires both acquisition/easement and restoration of potentially 4 parcels. Smaller project would be less complex. | 1 - High
(20) Salmonberry Creek from Constructed Side Channel Ponds to Long Lake Road | WA: Creek confined in a ditch. Restoration actions in this segment should aim to restore channel complexity, floodplain connectivity, and riparian conditions. ST: This project will move the creek out of the ditch that was constructed to drain agricultural lands. | Channel Complexity | Channel Restoration | Protection Riparian Wood | Tier 1 | B Medium Benefits | 1 | 2 | 1 | 1 | 0 | SCALE: Mainstem only: 500m, 10.1 acres Including connecting tributaries: 500m, 10.1 acres NOTES: 600m channelized in ditch. Some existing riparian vegetation from aerial imagery. Less benefit than reaches completely lacking shade, or lower reaches. | Coho Steelhead Cutthroat | 5 | 1 | 2 | 3 | 2 | SEQUENCING: Requires downstream project Barrier at AA14 (Baker Road). Barrier at Sedgwick Road planned for replacement 2021-2023. RESPONSE TIME: Side channel / meanders / wood placement give immediate additional habitat. Riparian restoration longer response time. COMPLEXITY: 8 parcels. Most of project area (400m) in 2 parcels. | 8 |  |  |  | Approx. 4 private landowners.

## 4. Passage
Project Description |  |  |  |  | Benefit Criteria
Action Area (AA) | Notes WA: Watershed Assessment, ST: Steelhead Recovery Plan | Steelhead Recovery Plan Category | Primary Strategy | Secondary Strategies | Tier | Benefit Category | Project Type | Scale 1 point per 1000m or 10 acres of habitat immediately accessed + half points for habitat potentially accessed following additional barrier removal | Habitat Quality Quality of habitat immediately accessed 1 = Low 2 = Medium 3 = High | Continuity 3 = Fills gap between high quality habitats 2 = Adjacent high quality habitat 1 = Not adjacent high quality habitat | Education | Benefit Notes | Target Species | BENEFIT SCORE | Sequencing Score 4 = required for upstream project 3 = increases benefits of upstream project 2 = Standalone or Cluster 1 = Requires downstream project | Response Time 3 = Short 2 = Moderate 1 = Long | Complexity 4 = Low 3 = Moderate 2 = High 1 = Very High | Estimated Cost | Implementation Notes | IMPLEMENTATION SCORE | Barrier ID | FeatureTyp | StreamName | TributaryT | Fish Use | Fish Use Criteria | RoadName | Barrier? | Barrier Reason | Percent Passable | Owner | Data Source | SurveyDate | LinealGain | PriorityIn | PotentialS | Report Link
(12) Salmonberry Creek Crossing at Clover Valley Road SE | WA: 8.5 foot diameter pipe arch culvert is undersized for location (33% passability) (15 foot bank full width). | Not listed | Passage |  | Tier 1 | A Highest Benefits | 2 | 10 | 2 | 1 | 0 | SCALE: Immediate: 1,700m, 11.1 acres Potential: 18,100m, 151.9 acres NOTES: Would increase access (from 33%) to Salmonberry Creek (Capacity). Located close to Long Lake. | Chum Coho Steelhead SR Cutthroat Resident Trout | 15 | 3 | 3 | 1 | 2 | SEQUENCING: Increases benefits of all upstream projects. Already significant investment upstream, as well as additional projects planned. RESPONSE TIME: Short for all passage projects. COMPLEXITY: County-owned road. Temporary road closure would cut off access to ~30 homes. | 9 | 999764 | Culvert | Salmonberry Cr | Long Lk | Yes | Mapped | Clover Valley Rd SE | Yes | Velocity | 33 | County | WDFW | 39581 |  |  |  | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/999764_Report.pdf
(14) Salmonberry Creek Crossing at SE Baker Road | WA: 2008 survey says culvert is impassable. 2015 reconnaissance noted culvert was backwatered so not creating a barrier. (0% or not a barrier) ST: Actions would replace the existing culvert with a bridge or larger culvert. County road? | Barrier | Passage |  | Tier 1 | B Medium Benefits | 2 | 11.5 | 3 | 2 | 0 | SCALE: Immediate: 5,800m, 51.4 acres Potential: 16,400m, 140.8 acres NOTES: Culvert replacement would potentially open up or improve access to most of Salmonberry Creek, although unclear if currently a barrier (Capacity). | Chum Coho Steelhead SR Cutthroat Resident Trout | 18.5 | 1 | 3 | 3 | 2 | SEQUENCING: Requires downstream project Increases benefits of all upstream projects. Already significant investment upstream, as well as additional projects planned. One downstream barrier (AA12, 33%). RESPONSE TIME: Short for all passage projects. COMPLEXITY: County-owned road. Detour possible during construction. | 9 | 999763 | Culvert | Salmonberry Cr | Long Lk | 10 Yes | 13 Mapped | SE Baker Rd | Yes | Slope | 0 | County | WDFW | 39580 |  |  | Chum, Coho, Steelhead, SR Cutthroat, Resident Trout | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/999763_Report.pdf
(17) Salmonberry Creek Crossing at SE Sedgwick Road | WA: 7.5 foot diameter arches culvert. Barrier due to 1.5 foot water surface drop on downstream side. (33% passability). ST: Actions would replace the existing culvert with a bridge or larger culvert. WSDOT Included on WSDOT Fish Passage Barrier Protection Plan. Construction planned 2021 - 2023. https://wsdot.wa.gov/projects/fishpassage/project-delivery-plan | Barrier | Passage |  | Tier 1 | B Medium Benefits | 2 | 9 | 1 | 1 | 0 | SCALE: Immediate: 8,100m, 71.4 acres Potential: 10,600m, 89.4 acres NOTES: Would increase access (from 33%) to approx. half of Salmonberry Creek. | Chum Coho Steelhead SR Cutthroat Resident Trout | 13 | 1 | 3 | 2 | 2 | SEQUENCING: Requires downstream project Two downstream barriers (AA12, AA14). RESPONSE TIME: Short for all passage projects. COMPLEXITY: WSDOT-owned. Major road. Detour available. | 8 | 990366 | Culvert | Salmonberry Cr | Long Lk | Yes | Biological | SR160 | Yes | WS Drop | 33 | State | WDFW | 39580 | 9210 | 32.51 | Chum, Coho, Steelhead, SR Cutthroat, Resident Trout | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/990366_Report.pdf
(21) Salmonberry Creek Crossing at Private Road Downstream of Long Lake Road | ST: This action would replace the existing crossing with a bridge or larger culvert. Private Road - Kitsap CD or other? WA: Private road crossing with 2 foot diameter culvert at a slope of 11%. WDFW 2008 assessment noted that the culvert was beginning to wash out. (0% passability) | Barrier | Passage |  | Tier 1 | B Medium Benefits | 2 | 1 | 1 | 2 | 0 | SCALE: Immediate: 0m, 0 acres Potential: 2,200m, 14 acres NOTES: Open access to 2,200m of habitat, currently impassable. | Chum Coho Steelhead SR Cutthroat Resident Trout | 6 | 1 | 3 | 3 | 3 | SEQUENCING: Cluster Three downstream barriers (AA12, AA14, A17). RESPONSE TIME: Short for all passage projects. COMPLEXITY: Privately owned, one landowner. Low complexity if willing landowner. | 10 | 999391 | Culvert | Salmonberry Cr | Long Lk | Yes | Biological |  | Yes | Slope | 0 | Private | WDFW | 39587 | 3146 | 24.01 | Chum, Coho, Steelhead, SR Cutthroat, Resident Trout | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/999391_Report.pdf
(22) Salmonberry Creek Crossing at Long Lake Road | WA: 3 foot diameter culvert. Barrier due to velocity. (67% passability). ST: This action would replace the existing crossing with a bridge or larger culvert. County Road? | Barrier | Passage |  | Tier 1 | C Lowest Benefits | 2 | 2 | 1 | 1 | 0 | SCALE: Immediate: 2,200m, 1.1 acres Potential: 2,200m, 1.1 acres NOTES: Improve access (from 67%) to AA23, through Howe Park and upstream reaches. | Chum Coho Steelhead SR Cutthroat Resident Trout | 6 | 2 | 3 | 3 | 2 | SEQUENCING: Cluster Four downstream barriers (AA12, AA14, A17, A21). RESPONSE TIME: Short for all passage projects. COMPLEXITY: County-owned. Detour available. | 10 | 999389 | Culvert | Salmonberry Cr | Long Lk | Yes | Biological | Long Lake Rd | Yes | Velocity | 67 | County | WDFW | 39582 | 3094 | 18.08 | Chum, Coho, Steelhead, SR Cutthroat, Resident Trout | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/999389_Report.pdf
(29) Upper Curley Creek | WA: Channel segment from Long Lake to crossing is channelized and incised. Mullenix Road crossing is impassable due to water surface drop. Recommend culvert replaced with bridge of larger culvert, and wood placement and riparian restoration. ST: "This action would replace the existing crossing with a bridge or larger culvert. BUT CHECK TO SEE IF THIS IS ABOVE STEELHEAD EXTENT!" Information from WFC 4/27/2021: WFC located a natural feature, ~500’ upstream of the SE Mullenix Rd crossing, that should be investigated as a potential natural barrier to fish passage. This feature appeared to be a zone of significant erosion and has a 10’ vertical drop between the upper and lower stream beds. Upstream, the channel runs subsurface for about 50’, reemerging at the base of the drop. | Barrier | Passage | Protection Riparian Wood | Tier 1 | B Medium Benefits | 2 | 1 | 3 | 1 | 0 | SCALE: Immediate: 150m, 0.2 acres (to natural barrier noted by WFC) Potential: 1,700m, 2.1 acres NOTES: Open access to approx. 500'. Total upstream length (past natural barrier) 1300m. Photos in culvert report indicate ephemeral stream. Barrier report lists multiple species. SalmonScape maps don't show use. Assume potential use if barrier removed, but confirm. | Coho Steelhead SR Cutthroat Resident Trout | 7 | 2 | 3 | 3 | 3 | SEQUENCING: Standalone No upstream projects. No downstream barriers. RESPONSE TIME: Short for all passage projects. COMPLEXITY: County-owned. Detour available. | 11 | 420081 | Culvert | Curley Cr | Long Lk | Yes | Physical | SE Mullenix Rd | Yes | WS Drop | 0 | County | WDFW | 42172 |  |  | Coho, Steelhead, SR Cutthroat, Resident Trout | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/420081_Report.pdf
(7) Unnamed Stream 15.0187 to Locker Road | Potentially current RCO funding for this project. SH to confirm. Weir replaced in 2014 with KCD funding. Partial barrier (67%) due to outfall drop and undersized low flow notch. WA: Near term recommendation: replace concrete control with additional weirs/logs to reduce drop. Longer term recommendation: removal of dam, restoration of floodplain and channel migration zone, riparian restoration, wood placement. ST: Actions include a replacement of the concrete control with additional weirs or log assemblage and the removal of the dam and restoration of floodplain and channel migration zone at the tributary confluence. | Barrier | Passage | Channel Restoration Protection Riparian Wood Passage | Tier 1 | B Medium Benefits | 2 | 3 | 2 | 3 | 0 | SCALE: Immediate: 3,200m, 5.3 acres Potential: 3,200m, 5.3 acres NOTES: Improve passability (from 67% to 100%, or still difficult with undersized low flow notch?) to entire length of tributary (approx. 2662m) (Capacity). Improved habitat conditions at confluence. | Coho Chum Steelhead | 10 | 3 | 3 | 3 | 2 | SEQUENCING: Increases benefits of upstream project No downstream barriers. This project will increase benefits of AA8, AA9, AA10 upstream. Increases benefits of upstream project. RESPONSE TIME: Short response for passage projects. Medium for channel complexity. COMPLEXITY: Private ownership (1 landowner, or up to 3 if include 2 smaller parcels close to Locker Rd). KCD project suggests willing landowner? No road closures required. | 11
(5) Banner Creek (15.0186) Crossing at Sedgwick Road | WA: 2.5 foot diameter culvert with length of 175 feet, 5% slope and 2.5 foot surface water drop. Recommend culvert replacement with wood placement upstream and downstream to prevent further incision. ST: This action would replace the existing crossing with a bridge or larger culvert. WSDOT ST: Large woody debris will be placed in the creek. Acquire land for conservation. | Barrier, Channel Complexity | Passage | Wood | Tier 1 | B Medium Benefits | 2 | 2 | 1 | 2 | 0 | SCALE: Immediate: 1,500m, 2.5 acres Potential: 1,500m, 2.5 acres NOTES: Culvert replacement would open access (currently 0%) to 837m habitat (Capacity, Diversity). Wood placement to re-establish channel complexity, promote sediment storage and prevent additional accelerated incision. Upstream habitat appears forested on aerial imagery. Not included in canopy height maps. | Coho Steelhead SR Cutthroat Resident Trout | 7 | 4 | 3 | 2 | 2 | SEQUENCING: Required for upstream project No downstream barriers. Upstream (AA6) proposed for protection, this project will be required to gain benefits in AA6. RESPONSE TIME: Short for all passage projects. COMPLEXITY: Major road; state ownership. | 11 | 991567 | Culvert | unnamed | Curley Cr | Yes | Mapped | SR 160 | Yes | WS Drop | 0 | State | WDFW | 40800 | 837 | 12.69 | Coho, Steelhead, SR Cutthroat, Resident Trout | http://apps.wdfw.wa.gov/fishpassagephotos/Reports/991567_Report.pdf

## 5. Protection
Project Description |  |  |  |  | Benefit Criteria | [9 empty] | Implementation Criteria
Action Area (AA) | Notes WA: Watershed Assessment, ST: Steelhead Recovery Plan | Steelhead Recovery Plan Category | Primary Strategy | Secondary Strategies | Tier | Benefit Category | Project Type | Scale 1 point per 1000m or 10 acre project footprint | Habitat Quality Quality of habitat protected 3 = High 2 = Medium 1 = Low | Continuity 3 = Fills gap between high quality habitats 2 = Adjacent high quality habitat 1 = Not adjacent high quality habitat | Outreach | Benefit Notes | Target Species | BENEFIT SCORE | Sequencing Score 4 = required for upstream project 3 = increases benefits of upstream project 2 = Standalone or Cluster 1 = Requires downstream project | Response Time 3 = Short 2 = Moderate 1 = Long | Complexity 4 = Low 3 = Moderate 2 = High 1 = Very High | Estimated Cost 3 = Low (<12.5 acre) 2 = Moderate 1 = High (>50 acres) | Implementation Notes | (Landowners per 1000m?) | IMPLEMENTATION SCORE | COMBINED SCORE
(2) Curley Creek Estuary to Sedgwick Road | Zoned Rural Protection. This reach includes GPC Tyner Preserve, and Williamson / Miller properties proposed for conservation. WA: Recovering forest in ravine. Riparian buffer in generally good condition except specific patches. Very limited wood. Given potential of riparian buffer to recruit wood, wood placement should be focused in areas with disturbed riparian buffer. ST: Native riparian vegetation will be restored and replaced in locations where it was removed. Additionally, large woody debris will be placed in the stream to improve channel complexity. Mentions CE. | Riparian | Protection | Riparian Wood | Tier 1 | B Medium Benefits | 3 | 3 | 3 | 2 | 0 | SCALE: Mainstem only: 2,600m, 18.8 acres Including connecting tributaries: 5,700m, 23.1 acres NOTES: Good riparian cover. Lower position in watershed. | Steelhead Coho Resident Coastal Cutthroat Chum | 11 | 2 | 2 | 1 | 2 | SEQUENCING: Standalone No downstream barriers. COMPLEXITY: GPC already active in this area. Approx. 15 additional private parcels in this area. (Approx. 2600m AA). COST: Estimating $200,000/10 acres | 5.7692 | 7 | 40
(4) Banner Creek (15.0186) to Sedgwick Road | WA: Well forested ravine should be protected by dedicating land for conservation. Field assessment required to assess wood loading. Relatively steep channel gradient makes this stream sensitive to channel incision with increases in runoff from contributing watershed. | Not listed | Protection | Wood | Tier 1 | B Medium Benefits | 3 | 1 | 3 | 2 | 0 | SCALE: Mainstem only: 1,200m, 2.8 acres Including connecting tributaries: 2,100m, 3.4 acres NOTES: Expect this area to have cooler water temperatures based on good forest cover. May provide valuable thermal refuge. Lower position in watershed. | Coho Chum | 9 | 2 | 2 | 2 | 3 | SEQUENCING: Standalone No downstream barriers. COMPLEXITY: Approximately 8 landowners. (Approx. 1200m AA) | 6.6667 | 9 | 36
(06) Banner Creek (15.0186) Upstream of Sedgwick Road | Zoned Rural Protection. ST: Land will be dedicated for habitat protection. These part of the creek contains several tributaries near the headwaters, and protecting this land will prevent impacts from land use. WA: The channel segment upstream of Sedgwick Road is less steep than the ravine segment downstream and is connected with several small tributaries forming the headwaters of this creek. The stream corridor should be protected from land use impacts by dedicating land for habitat protection. | Land Use | Protection |  | Tier 1 | B Medium Benefits | 3 | 1 | 2 | 1 | 0 | SCALE: Mainstem only: 700m, 2 acres Including connecting tributaries: 1,500m, 2.5 acres NOTES: There is no water temperature data for this area, but would expect to have lower water temperatures due to forest cover. Potential to provide thermal refuge, if downstream barrier removed. Higher position in watershed (headwaters of lower positioned tributary). | [Barrier removal required] | 7 | 1 | 2 | 2 | 3 | SEQUENCING: Requires downstream project Sedgewick Rd culvert is a complete barrier (AA 5). COMPLEXITY: Approximately 7 landowners based on mapped tributaries. (Approx. 700m AA) | 10 | 8 | 29
(08) Unnamed Stream 15.0187 in Ravine Upstream of Locker Road | Zoned Rural Protection. ST: Land will be dedicated for habitat protection. Large woody debris will be placed to enhance stream habitat. This is a steep stream that flows through a forested area, and the protection of this land will prevent channel incision and increased sediment loads. WA: The stream corridor is forested and should be protected. Field assessment recommended to assess wood loading. Absent sufficient wood loading, channel incision will undercut steep hillslopes of the ravine disrupting sediment dynamics and resulting in excessive sedimentation in lower gradient areas. | Land Use | Protection | Wood | Tier 1 | B Medium Benefits | 3 | 1 | 3 | 1 | 0 | SCALE: Mainstem only: 900m, 1.5 acres Including connecting tributaries: 900m, 1.5 acres NOTES: Protect processes of well forested area. Immediately upstream of Williamson property proposed for conservation, and AA2. Lower position in watershed. | Coho Chum Steelhead likely | 8 | 1 | 2 | 1 | 3 | SEQUENCING: Requires downstream project Improvements to Williamson fish ladder would improve access. COMPLEXITY: Proximity to current GPC projects. 14 landowners. (Approx. 900m AA) | 15.5556 | 7 | 31
(09) Unnamed Stream 15.0187 near Frog Pond Road | Zoned Rural Protection. WA: Recommend field assessment of channel conditions, habitat protection encompassing off-channel wetlands, placement of wood and riparian restoration. ST: Riparian vegetation will be restored to promote future wood recruitment. Acquire land for conservation. | Riparian | Protection | Riparian Wood placement | Tier 1 | A Highest Benefits | 3 | 1 | 2 | 3 | 0 | SCALE: Mainstem only: 900m, 1.5 acres Including connecting tributaries: 900m, 1.5 acres NOTES: Established riparian buffer provides shade. | Coho Resident Coastal Cutthroat Potentially Chum and steelhead | 9 | 1 | 2 | 3 | 3 | SEQUENCING: Requires downstream project Improvements to Williamson fish ladder would improve access. COMPLEXITY: 3 private parcels (400m AA) | 3.3333 | 9 | 36
(10) Headwaters of Unnamed Stream 15.0187 | Zoned Rural Residential and Rural Protection. ST: Land will be dedicated for habitat protection. Large woody debris will be placed to enhance stream habitat. This area is well forested and land conservation will protect this habitat in the future. WA: The upper segment of this tributary flows from west to east and steepens in gradient compared to the downstream reach. Drainage from a developing residential area off of Mile Hill Road contributes runoff to the stream. The stream corridor is generally well forested and should be protected by dedicating land for habitat protection. Wood placement is recommended to provide channel stability and prevent incision associated with land use impacts to peak flows. | Land Use | Protection | Wood | Tier 1 | A Highest Benefits | 3 | 1 | 3 | 1 | 0 | SCALE: Mainstem only: 1,400m, 2.3 acres Including connecting tributaries: 1,400m, 2.3 acres NOTES: Protection can buffer pollutants, moderate flows from development around SE Mile Hill Dr. Higher position in watershed (headwaters of lower positioned tributary). | Coho Steelhead likely Cutthroat? | 8 | 1 | 2 | 1 | 3 | SEQUENCING: Requires downstream project Improvements to Williamson fish ladder would improve access. COMPLEXITY: 10 landowners in this AA. Can do this in conjunction with AA9. (1400m AA) | 7.1429 | 7 | 31
(13) Salmonberry Creek from Clover Valley Road to Baker Road | Zoned Rural Protection. WA: Stream corridor is recovering from past clearing and is relatively well forested in some locations. Protect areas with quality riparian cover; restore riparian conditions in impacted areas. ST: Riparian vegetation will be restored along with wood placement to create channel complexity. | Riparian | Protection | Riparian Wood | Tier 1 | A Highest Benefits | 3 | 1 | 2 | 1 | 0 | SCALE: Mainstem only: 800m, 9.7 acres Including connecting tributaries: 1,700m, 11.1 acres NOTES: Lower position in watershed (close to Long Lake) Haring (2000) noted high quality wetlands in this reach, including several small tributaries and good gravels. Some riparian shade (mostly 10 - 50' height, patchy 50+feet). | All | 7 | 1 | 2 | 1 | 3 | SEQUENCING: Requires downstream project One partial barrier downstream (AA12). COMPLEXITY: Upstream portion has approx. 15 parcels (larger on west, smaller on east). Downstream portion is within one large parcel. (Approx. 750m creek in AA). | 18.75 | 7 | 28
(15) Salmonberry Creek from Baker Road to Cool Creek confluence | Zoned Rural Protection. WA: Flows through narrow valley bottom forested along channel margin. Overall condition is better than other segments. Contains relatively large shrub-scrub wetland complex with beaver activity. ST: This project will protect the stream corridor through conservation easements. This action will preserve the wetland area at the confluence of cool creek. | Land Use | Protection |  | Tier 1 | A Highest Benefits | 3 | 1 | 3 | 2 | 0 | SCALE: Mainstem only: 800m, 14.7 acres Including connecting tributaries: 1,800m, 16.1 acres NOTES: Overall better condition. Contains wetland complex. Lower position in watershed (close to Long Lake). Mapped canopy height 0-10'. | Coho Chum Steelhead | 9 | 1 | 2 | 2 | 2 | SEQUENCING: Requires downstream project Two partial barriers downstream (AA12, AA14) COMPLEXITY: 7 parcels with creek on boundary. 2 larger parcels. (800m AA). | 8.75 | 7 | 34
(18) Salmonberry Creek between Sedgwick Road and Salmonberry Road | Zoned Rural Protection and Urban Low Residential (5-9 Du/acre) (Creek within or very close to 5 UL lots). WA: Stream corridor is well forested. Riparian and channel conditions should be inspected. If natural wood recruitment is unlikely given riparian conditions, recommend wood placement. ST: This project will protect the stream corridor through conservation easements. This portion of the stream is well forested and this action will promote continued natural recruitment of large woody debris. | Land Use | Protection |  | Tier 1 | A Highest Benefits | 3 | 1 | 2 | 1 | 0 | SCALE: Mainstem only: 800m, 13.0 acres Including connecting tributaries: 1,100m, 13.4 acres NOTES: Highest value for protecting functions in and around UGA. Water monitoring site on upstream end of this AA shows high temperatures. Protection of forest will mitigate high temperatures from upstream deforested reaches. (Includes patches with canopy height >100'). Haring (2000) noted this areas was reported to be high quality with good gravels. Highest position in watershed. | Coho Steelhead | 7 | 1 | 3 | 1 | 3 | SEQUENCING: Requires downstream project Three partial barriers downstream (AA12, AA14, AA17) RESPONSE TIME: Short response time due to location in UGA (assume higher development pressure). COMPLEXITY: Many small parcels (approx. 12 parcels in 800m AA). COST: Anticipate higher costs in UGA. | 15 | 8
(25) Cool Creek upstream of Phillips Road | Zoned Rural Residential (1 DU/5ac), RP (1 DU/10ac), Urban Low Residential (5-9 DU/ac), Urban Restricted (1-5 DU/ac) ST: Wood will be placed in the stream within the Port Orchard UGA. WA: Relatively well established riparian corridor and should be protected. Wood placement recommended to increase channel complexity and stabilize the channel. | Channel Complexity | Protection | Wood | Tier 1 | A Highest Benefits | 3 | 2 | 3 | 2 | 0 | SCALE: Mainstem only: 1,600m, 2.7 acres Including connecting tributaries: 2,000m, 3.4 acres NOTES: Cool creek input keeps lower salmonberry creek cooler. Important to maintain thermal refuge within this habitat, and maintain lower salmonberry creek temperatures. Canopy height mostly 10-50', and 50+ feet. Mapped as wetland complex - not sure of condition. Second highest position in watershed. | Coho Chum Steelhead likely | 10 | 1 | 3 | 1 | 3 | SEQUENCING: Requires downstream project Two partial barriers downstream (AA12, AA14) RESPONSE TIME: Short response time due to location in UGA (assume higher development pressure). COMPLEXITY: 14 parcels including 1 larger parcel. COST: Anticipate higher costs in UGA. | 8.75 | 8
(27) Tributary Channels Draining Urban Growth Area | WFC is currently doing water typing surveys throughout watershed. WA: Several small tributaries drain upland hillslope areas, including within UGA. Field reconnaissance indicates gaps in WDNR water type map. ST: This project will map tributary channels to identify their location, and define a riparian corridor around the channels. These actions will protect the tributary channels from future disturbance and support existing riparian vegetation. | Land Use | Protection | Riparian Wood | Tier 1 | A Highest Benefits | 3 | 1 | 2 | 1 | 0 | SCALE: Area proposed for protection: 150m, 0.2 acres. Total AA (including areas already protected): Mainstem only: 1,100m, 1.7 acres; Including connecting tributaries: 1,100m, 1.7 acres NOTES: Benefits come from protecting existing functions. | Potentially Coho, Steelhead, Cutthroat | 7 | 1 | 2 | 2 | 3 | SEQUENCING: Requires downstream project 2 - 3 downstream barriers on Salmonberry Creek. COMPLEXITY: WFC is currently doing water typing surveys. Coverage is limited by landowner permissions. 7 unprotected parcels on mapped streams; potentially more streams not yet mapped. | 46.6667 | 8
(30) Additional Tributaries draining to Long Lake | WA: Further evaluation of riparian and channel conditions required. Protect areas with functioning riparian conditions. Correct fish passage barriers when tributaries cross Mullenix Road. Further information from WFC surveys: . CU25- Unnamed stream located on the south end of Long Lake (Listed on the Curley creek restoration priority matrix, but additional information was requested from WFC surveys) a. Restoration opportunity: Replace Full barrier culvert at Mullenix Rd crossing (WDFW Barrier ID: 420083). A rainbow trout smolt was caught at the culvert outlet, but no fish were observed in the upstream reach. i. Replacing this culvert would allow fish passage to 2,200 ft of known type F habitat upstream. The stream is spring fed, flowing through a steep sided ravine forested with mature conifers and deciduous trees. development does exist upslope on both banks, but a wide, intact riparian corridor exists throughout the reaches surveyed by WFC. WFC surveys have also demonstrated that the channel has characteristics similar to where fish were documented downstream, qualifying it for type F classification upstream beyond the WDNR mapped type F/N break, and aligning with the habitat quality and habitat type observed in other streams within the Curley basin where fish were brought to hand by WFC. ii. An additional barrier culvert exists, ~2,200 ft upstream of the Mullenix Rd crossing, at the Lawrence Dr SE crossing. WFC surveys show that type F habitat extends 200 ft upstream of this crossing. Though beyond that point, water type is unknown due to lack of access. iii. Although a wide riparian buffer exists between the stream and upslope development, WFC observed signs of excess erosion within the channel, where the stream was incised up to 5 ft in some locations. This could be related to stormwater, and a topic of future investigation/mitigation/restoration. 2. CU17.1-An unnamed, and previously unmapped, stream located on the north end of Long Lake. a. The lower reach of this stream (~800’), and its confluence with Long Lake, are located within Long Lake County Park. There are two failed culverts within the park that limit upstream fish passage. Numerous juvenile coho were observed below the failed culverts during WFC’s site revisit in 2021. The stream flows through the park in a narrow riparian corridor lined with alder. A gravel access road follows along the left bank with a gravel parking area located beyond the narrow riparian corridor on the right bank. i. Restoration opportunity: improve fish passage, establish a wider riparian buffer, improve habitat complexity within the channel. b. There is a full barrier culvert upstream of Long Lake County Park, at the crossing of Long Lake Rd SE. Fish were observed in the plunge pool of this culvert, but nowhere else in the upstream channel. Much of the upstream channel surveyed by WFC had been ditched or modified in some way, including a 500’ length of channel that was diverted and ditched along Long lake Rd SE. The upper channel could be the focus of future restoration, but the lower channel, in the park, would likely be higher priority. 5. CU15, CU17- two unnamed type F streams a. These two streams are located on the north end of Long Lake. CU15 enters the right bank of Curley creek not too far downstream of the outlet of Long Lake. CU17 enters Long Lake near the outlet/ beginning of the Curley creek channel. The lower ends of these streams flow through two properties (to the SE of Long Lake Rd) with large open fields, and appear to have been, at one time, ditched along opposite property lines. There is opportunity to reestablish a riparian buffer, re-meander the channel, and improve channel complexity in these areas. Numerous juvenile salmonids were observed in the upper reaches of both streams. WFC identified an additional stream of the south end of the property. | Not listed | Protection | Passage | Tier 1 | B Medium Benefits | 3 | 2 | 2 | 1 | 0 | SCALE: Mainstem only: 1863m, 4.6 acres Tributaries: 1863m, 4.6 acres NOTES: Passage project from correction of culvert on tributary between Upper Curley Creek and wetland complex would open access to approx. 600m, including an area mapped as 50' to 100' canopy height. More information on functions to be protected in this area may come from WFC water typing surveys. | Coho Steelhead SR Cutthroat Resident Trout | 8 | 2 | 2 | 1 | 3 | SEQUENCING: Cluster Coordinate passage correction with replacement of culvert at Upper Curley Creek (AA 29). COMPLEXITY: Many small parcels (26). This Action Area covers many small tributaries around Long Lake, so could be implemented as many smaller projects. | 5.2 | 8
(31) Wetland Complex at SE corner of Long Lake | Little information was found to characterize the wetland complex. Recommend further protection of existing functions, and further assessment. | Not listed | Protection | Passage | Tier 1 |  | 3 | 1 | 3 | 1 | 0 | SCALE: Mainstem only: 1,200m, 1.9 acres Including connecting tributaries: 1,200m, 1.9 acres NOTES: TBC - More information on functions to be protected in this area may come from WFC water typing surveys in this area. | Salmon use not mapped in this area. | 8 | 2 | 2 | 3 | 3 | SEQUENCING: Standalone No downstream barriers. COMPLEXITY: One large parcel closest to lake owned by HOA. Approx. 8 additional residential parcels upstream. | 6.6667 | 10

## 6. Other
Project Description |  |  |  |  | Benefit Criteria | [9 empty] | Implementation Criteria
Action Area (AA) | Notes WA: Watershed Assessment, ST: Steelhead Recovery Plan | Steelhead Recovery Plan Category | Primary Strategy | Secondary Strategies | Tier | Benefit Category | Project Type | Scale Score | Habitat Quality Quality of habitat restored (Low = 3) or protected (High = 3) | Connectivity 3 = Directly adjacent a quality area 2 = <1000 m from high quality 1 = >1000 m from high quality | Outreach | Benefit Notes | Target Species | BENEFIT SCORE | Sequencing Score 2 = required for / increases benefits of upstream project 1 = Standalone 0 = Requires downstream project | Response Time 3 = Short 2 = Moderate 1 = Long | Complexity 4 = Low 3 = Moderate 2 = High 1 = Very High | Estimated Cost 3 = Low 2 = Moderate 1 = High | Implementation Notes | IMPLEMENTATION SCORE
(28) Long Lake Shoreline | WA: Sedimentation and eutrophication are ongoing issues. The lake is listed as a Category 5 (polluted water requiring a TMDL) water body for phosphorus under Section 303(d) of the Clean Water Act. Study from 1998 - 2000 indicates large mouth bass likely have a substantial impact on coho smolt production. Recommendations: > Protect remaining areas of undeveloped shoreline. > Revegetate impacted shoreline. > Control input of nutrients and pesticides from surrounding land. > Assess and manage predation impacts. ST: This project will repair riparian habitat, and develop strategies to reduce the input of nutrients and pesticides into the lake. Create long term management plan for nutrient and pesticide inputs. | Riparian | Protection Riparian Nutrient/pesticide management Predation management |  | Tier 1 | A Highest Benefits | 1 | 34 | 3 | 3 | 1 | SCALE 336.3 acres NOTES: Potential to greatly improve productivity by reducing predation pressure, if findings of past study still hold true. Currently low quality habitat to be restored. Not connected to high quality habitat, but used by all fish migrating to Salmonberry Creek, SE wetlands etc. | Coho especially, also others | hi | 1 | 2 | 1 | 2 | SEQUENCING: Standalone No downstream barriers. RESPONSE TIME: Response time varies for each action. COMPLEXITY: Projects could be split into multiple lower complexity projects. Politically challenging location. | 6
Watertyping and Enforcement | Water typing and subsequent monitoring and enforcement of regulations | NA | Protection |  | Tier 1 |  | 1 | 9 | 3 | 3 | 1 | NOTES: Underpins all protection measures. WFC suggests that water typing maps may underestimate the actual miles of fish-bearing waters by 20%, based on findings in Blackjack Creek Watershed. Curley Creek watershed includes 46 km of waters (including Long Lake). Assuming 20% more fish bearing streams are identified this project has an estimated scale of 9.2km. | All | 16 | 1 | 2 | 1 | 3 | SEQUENCING: Standalone RESPONSE TIME: Benefit to processes within 5 years. COMPLEXITY: Very high complexity due to number of landowners, although landowners likely more willing than a restoration / acquisition project because only agreeing to site survey. | 7
(1) Curley Creek Estuary and Nearshore | WA: The nearshore area of Yukon Harbor is extensively developed and the shoreline is highly modified. Actions to prevent further shoreline armoring and remove existing armor are needed to allow for natural shoreline adjustments to sea level rise anticipated in Puget Sound. Estuary upstream of the bridge is protected through GPC acquisitions. ST: This project will identify shoreline armoring to be removed or replaced with soft shorelines, identify houses and structures to be moved away from shorelines, encourage compliance with the SMP, encourage the use of natural vegetation, and restore riparian habitats. | Channel Complexity | Shoreline softening | Protection Riparian Relocate structures Compliance | Tier 1 | B Medium Benefits | NA | NA | NA | NA | NA | This Action Area was excluded from the assessment. The recommended actions related to restoration in Yukon Harbor. These actions are prioritized at a regional scale through the East Kitsap Nearshore Prioritization Assessment. The regional scale is more appropriate than a watershed scale for these projects, because fish using the Curley Creek watershed will use nearshore habitats throughout the region. | NA | NA | NA | NA | NA | NA | This Action Area was excluded from the assessment. The recommended actions related to restoration in Yukon Harbor. These actions are prioritized at a regional scale through the East Kitsap Nearshore Prioritization Assessment. The regional scale is more appropriate than a watershed scale for these projects, because fish using the Curley Creek watershed will use nearshore habitats throughout the region. | NA

## 7. Criteria
Prioritization Criteria
BENEFIT CRITERIA
Score | Description | Rationale
Project Type
3 | Protection Projects | Based on literature identifying protection as the first priority (Beechie et al), and findings of IWMs that passage projects consistently have measurable benefits.
2 | Passage Projects
1 | Channel Complexity
Score | Description | Rationale
Scale
1+ | One point per 1000m or 10 acres of habitat, with project footprint rounded to the nearest 1000m or 10 acres. Scale of restoration and protection projects refers to project footprint. Scale of passage projects refers to the area of habitat accessed after barrier removed. Full points were given to habitat immediately accessed, and half points were given to habitat with potential to be accessed if all upstream barriers are removed. | The highest score from either length or area applied. Area mapped as FEMA 1% annual chance of occurrence floodplain layer, or where FEMA map doesn't cover a reach, a 5m buffer to the streamline. Scale from mainstem only, not smaller connecting streams (e.g. for an Action Area on Banner Creek, Banner Creek is considered mainstem).
Score | Description | Rationale
Habitat Quality - for Protection and Passage Projects
3 | High - Habitats with minimal disturbance, native riparian vegetation with good canopy cover, moderate to high channel complexity. Nowhere is perfect - these areas typically have little to no wood. | Habitat quality mapped based on field observations noted in watershed assessment and qualitative input from partners. Categories are relative across the watershed. High quality habitats scored highest for protection and passage projects, but lower quality habitats scored highest for restoration projects (i.e. most room for improvement).
2 | Medium - Some high quality habitat elements, but other aspects degraded.
1 | Low - Channelized, low complexity, limited riparian canopy cover, little or no wood.
Score | Description | Rationale
Habitat Quality - for Restoration Projects
3 | Low | See description above.
2 | Medium
1 | High
Score | Description | Rationale
Habitat Continuity
3 | Fills gap between high quality habitats | Reflects benefit of creating contiguous reaches of good quality habitat.
2 | Adjacent high quality habitat
1 | Not adjacent high quality habitat
IMPLEMENTATION CRITERIA
Score | Description | Rationale
Sequencing Considerations
4 | Required for upstream project Does the action need to be constructed before other high priority actions to facilitate achievement of their benefits? | From original Watershed Assessment Prioritization Framework
3 | Increases benefits of upstream project
2 | Cluster or Standalone: Is the action part of a “cluster” of other actions that need to be addressed as a whole? Can the action be constructed as “stand alone?”
1 | Requires downstream project: Does the action need to be constructed after other high priority actions because it is dependent on their processes to achieve its benefits?
Red flag | Will preclude higher priority action: Will the action preclude a higher biological priority action that is not currently feasible?
Score | Description | Rationale
Response Time
3 | Short Response Time Species are present in the reach or immediately downstream and experience full benefit immediately following implementation (e.g., culvert replacement for fish passage). | From original Watershed Assessment Prioritization Framework
2 | Moderate Response Time Action will have an immediate benefit to restoration of habitat forming processes at reach scale, species may now access previously inaccessible areas and improvement in survival would be observed within approximately 5 years following implementation (e.g., placement of large woody material, removal of constraints to lateral migration)
1 | Long Response Time Restoration of habitat forming processes depend on long-term maturation of strategy; species may be slow to respond to the restored habitat or habitat elements will take time to develop to the point of being beneficial; species experience benefits within 10+ years following implementation (e.g., riparian restoration).
Score | Description | Rationale
Complexity
4 | Low Relatively simple permitting Single property ownership (E.g. Kitsap County or Suquamish Tribe) for conservation | The definitions from the original Watershed Assessment Prioritization Framework were adapted to better differentiate between Action Areas. The vast majority of action areas include multiple private landowners which would have resulted in most being ranked High complexity. These were updated
3 | Moderate <5 private landowners. More involved permitting / includes in-water work. Includes work on a county-owned road.
2 | High <10 private landowners. Complex permitting process involving multiple federal, state and local government agencies; complex design and construction. Includes work on a state-owned road.
1 | Very High 10+ landowners. Includes work on a road with no available detour.
Score | Description | Rationale
Cost
3 | Less than $250,000 > Uses low cost techniques (e.g., replacement small culverts, focused riparian planting actions) > Minimal excavation and hauling distance of spoils > Little to no planting or weed control > No dewatering required > Easy access conditions | Definitions from Watershed Assessment Prioritization Framework. For protection projects, used a very rough cost estimate of $200,000 per 10 acres conserved (either CE or fee simple) based on costs of Childers Property and Estuary in Salmon Recovery Portal.
2 | $250,000 to $1,000,000 > Uses moderate cost techniques (e.g., replacement moderate size culverts, focused removal artificial constraints to lateral connectivity, typical log jam structures) > Moderate to high excavation and hauling distance of spoils > Planting or invasive weed control ranging from typical to complex > No dewatering requirements to standard requirements > Moderate access conditions
1 | Greater than $1,000,000 > Uses high cost techniques (e.g., replacement large size stream crossings, extensive removal artificial constraints to lateral connectivity, highly engineered log jams, extensive channel contouring) > Deep excavation or long distance hauling of spoils > Entails construction of additional new flood control or bank erosion features > Extensive planting or invasive weed control over several years > Intensive dewatering requirements > Limited, difficult, or remote access
ITEMS NOT INCLUDED IN CRITERIA
Item | Description | Rationale for exclusion
Limiting factors | Considered awarding points for projects that addressed a limiting factor for salmon | This criteria was discussed in partner meetings #2 and #3. It was found that scoring by limiting factor didn't differentiate between projects. Each of the actions recommended in the Watershed Assessment addressed at least one, but typically multiple ecological concerns and the extent that an action addresses limiting factor is related to the action's scale. For example, the Steelhead Recovery Plan identifies 10 ecological concerns that encompass the different conditions that directly impact salmonids as: habitat quantity, riparian condition, peripheral and transitional habitats, channel structure and form, water quality and water quantity. The plan also notes 2011 Biological Review Team identified degradation and fragmentation of freshwater habitat, with consequential effects on connectivity as the primary limiting factors and threats facing Puget Sound Steelhead.
Location in watershed | Considered awarding points based on location in the watershed. This could be higher points for upper watershed, due to the importance of headwater functions, or higher points for lower parts of the watershed where more species and more individuals would use that habitat. | This criteria was discussed in partner meeting #2. Partners somewhat agreed to strongly disagreed that this should be a criteria, and were split between where to prioritize headwaters or downstream habitats. The only position-related approach that was agreed on by the group was that downstream passage projects should be prioritized before upstream projects. This was incorporated into the ranking by through 'Sequencing' criteria.
Salmon species impacted | Giving higher points for reaches with more salmon species, or listed salmon species. | The species that would benefit from a project are listed in Sheets 3 - 6, but weren't included in the scoring. It can be assumed that steelhead will be present throughout the watershed, so scoring for listed-species presence doesn't differentiate between action areas. Scoring higher for a higher number of species would give lower reaches with chum more points than higher reaches that provide important watershed functions.
Climate Change | Awarding higher points to projects that would ameliorate the impact of climate change or increase resiliency, and deducting points for projects where climate change would reduce an action's affect, based Beechie et al 2013. | Each of the actions can be considered to increase resiliency, so this criteria didn't help differentiate between action areas.

## Additional Project Opps
Project Description | [6 empty] | Benefit Criteria
Action Area (AA) | Notes WA: Watershed Assessment, ST: Steelhead Recovery Plan | Action |  | Steelhead Recovery Plan Category | Primary Strategy | Secondary Strategies | Tier | Benefit Category | Project Type | Scale 1 point per 1000m or 10 acres of habitat immediately accessed + half points for habitat potentially accessed following additional barrier removal | Habitat Quality Quality of habitat immediately accessed 1 = Low 2 = Medium 3 = High | Continuity 3 = Fills gap between high quality habitats 2 = Adjacent high quality habitat 1 = Not adjacent high quality habitat | Education | Benefit Notes | Target Species | BENEFIT SCORE | Sequencing Score 4 = required for upstream project 3 = increases benefits of upstream project 2 = Standalone or Cluster 1 = Requires downstream project | Response Time 3 = Short 2 = Moderate 1 = Long | Complexity 4 = Low 3 = Moderate 2 = High 1 = Very High | Estimated Cost | Implementation Notes | IMPLEMENTATION SCORE | Barrier ID | FeatureTyp | StreamName | TributaryT | Fish Use | Fish Use Criteria | RoadName | Barrier? | Barrier Reason | Percent Passable | Owner | Data Source | SurveyDate | LinealGain | PriorityIn | PotentialS | Report Link
AA30 - addition | WFC Observations: 1. CU25 - Unnamed stream located on the south end of Long Lake (Listed on the Curley creek restoration priority matrix, but additional information was requested from WFC surveys) a. Restoration opportunity: Replace Full barrier culvert at Mullenix Rd crossing (WDFW Barrier ID: 420083). A rainbow trout smolt was caught at the culvert outlet, but no fish were observed in the upstream reach. i. Replacing this culvert would allow fish passage to 2,200 ft of known type F habitat upstream. The stream is spring fed, flowing through a steep sided ravine forested with mature conifers and deciduous trees. development does exist upslope on both banks, but a wide, intact riparian corridor exists throughout the reaches surveyed by WFC. WFC surveys have also demonstrated that the channel has characteristics similar to where fish were documented downstream, qualifying it for type F classification upstream beyond the WDNR mapped type F/N break, and aligning with the habitat quality and habitat type observed in other streams within the Curley basin where fish were brought to hand by WFC. ii. An additional barrier culvert exists, ~2,200 ft upstream of the Mullenix Rd crossing, at the Lawrence Dr SE crossing. WFC surveys show that type F habitat extends 200 ft upstream of this crossing. Though beyond that point, water type is unknown due to lack of access. iii. Although a wide riparian buffer exists between the stream and upslope development, WFC observed signs of excess erosion within the channel, where the stream was incised up to 5 ft in some locations. This could be related to stormwater, and a topic of future investigation/mitigation/restoration. | Correct Mullenix Road complete barrier | NA | NA | Passage |  |  |  | 2 | 1 | 2 | 3 | 0 | Would open access to 670m of good quality habitat. Habitat quality: WFC notes wide intact riparian corridor with mature coifers, and similar channel characteristics to where fish noted downstream. Signed of excess erosion; stream incised up to 5ft in some locations. |  | 8 | 2 | 3 | 3 | 2 | County owned road. | 10
CU17 | 1-An unnamed, and previously unmapped, stream located on the north end of Long Lake. a. The lower reach of this stream (~800’), and its confluence with Long Lake, are located within Long Lake County Park. There are two failed culverts within the park that limit upstream fish passage. Numerous juvenile coho were observed below the failed culverts during WFC’s site revisit in 2021. The stream flows through the park in a narrow riparian corridor lined with alder. A gravel access road follows along the left bank with a gravel parking area located beyond the narrow riparian corridor on the right bank. i. Restoration opportunity: improve fish passage, establish a wider riparian buffer, improve habitat complexity within the channel. b. There is a full barrier culvert upstream of Long Lake County Park, at the crossing of Long Lake Rd SE. Fish were observed in the plunge pool of this culvert, but nowhere else in the upstream channel. Much of the upstream channel surveyed by WFC had been ditched or modified in some way, including a 500’ length of channel that was diverted and ditched along Long lake Rd SE. The upper channel could be the focus of future restoration, but the lower channel, in the park, would likely be higher priority. | Correct two culverts within Long Lake County Park. Stream restoration within park (widen riparian buffer and in stream complexity) | Length of stream within County Park
AA 16 (Note 4) | a. There is a failed steel bridge located just south of Salmonberry creek’s crossing of SW Sedgwick Rd on a small piece of property owned by Steven Childers. The right bank footings of this bridge have eroded, and the right side of the bridge is resting on the streambed. The bridge does not appear to limit fish passage, at least at the time of the survey, but it would probably be a good idea to remove it before the entire structure falls into the channel. | Replace bridge on private property | NA
CU15, CU 17 | a. These two streams are located on the north end of Long Lake. CU15 enters the right bank of Curley creek not too far downstream of the outlet of Long Lake. CU17 enters Long Lake near the outlet/ beginning of the Curley creek channel. The lower ends of these streams flow through two properties (to the SE of Long Lake Rd) with large open fields, and appear to have been, at one time, ditched along opposite property lines. There is opportunity to reestablish a riparian buffer, re-meander the channel, and improve channel complexity in these areas. Numerous juvenile salmonids were observed in the upper reaches of both streams.